## Product Backlog
ID | Epic | User story |  |  | Acceptance Criteria | Priority | Sprint | Owner | Status | Defonition of Done | Iteration | Estimate (poonts)
|  | As a/an... | I want to be able to... | So that...
1 | Register Your Own Account | New user (New staff) | register a new account | I can log in now and for later | Given that I am a new user, when I go to the "Đăng ký" page: 1. Enter full name, username, password, confirm password, email address and click on the "Tạo tài khoản" button, then my information is sent to the admin account to wait for approval on my first login and I will be redirected to a login page with a message pop-up "Đăng ký thành công!". 2. Click in the input box but do not fill it out or leave username empty and click on the "Tạo tài khoản" button, then an error message will be displayed “Bạn cần nhập tên người dùng!” 3. Click in the input box but do not fill it out or leave password empty and click on the "Tạo tài khoản" button, then an error message will be displayed “Bạn cần nhập mật khẩu!” 4. Click in the input box but do not fill it out or leave email empty and click on the "Tạo tài khoản" button, then an error message will be displayed “Bạn cần nhập địa chỉ email khôi phục mật khẩu!” 5. Click in the input box but do not fill it out or leave confirm password empty and click on the "Tạo tài khoản" button, then an error message will be displayed “Bạn cần nhập xác nhận mật khẩu!” 6. Click in the input box but do not fill it out or leave full name empty and click on the "Tạo tài khoản" button, then an error message will be displayed “Bạn cần nhập họ tên!” 7. Click in the input box but do not fill it out or enter incorrectly confirm password and click on the "Tạo tài khoản" button, then an error message will be displayed “Bạn cần nhập đúng xác nhận mật khẩu!” 8. Enter wrong email format (without @) then an error message will be displayed “Email sai định dạng!” | high | 1 | FE, BE, UI | Done
2 | User Management | User (Boss, Leader, Staff) | log in to the system | I can use all the authenticated functions | Given that I am a registered user, when I go to the "Đăng nhập" page: 1. Enter my username and password correctly, click on the "Đăng nhập" button, then I can navigate to the home page of users with a message pop-up "Đăng nhập thành công!" 2. Enter an correct password but an incorrect username and click on the "Đăng nhập" button, then log in fails with an error message “Bạn cần nhập đúng tên người dùng và mật khẩu!” 3. Enter an correct username but an incorrect password and click on the "Đăng nhập" button, then log in fails with an error message “Bạn cần nhập đúng tên người dùng và mật khẩu!” 4. Enter an correct password but leave username empty and click on the "Đăng nhập" button, then log in fails with an error message “Bạn cần phải nhập tên người dùng!” 5. Enter an correct username but leave password empty and click on the "Đăng nhập" button, then log in fails with an error message “Bạn cần phải nhập mật khẩu!” | high | 1 | FE, BE, UI | Done
3 |  | User (Boss, Leader, Staff) | logout my account | I can leave the site | Given that I am a registered user and logged on, if I click on the avatar button and click on "Đăng xuất" button, then I will see a confirmation pop up "Bạn có chắc chắn muốn đăng xuất không?": 1. Click on "OK" button, then I will log out of the current account and be redirected to the login page. 2. Click on "Cancel" button, then I will remain on the current page. | high | 1 | FE, BE, UI | Done
4 |  | User (Boss, Leader, Staff) | reset a new password | I can log in to use all the authenticated functions | Given that I am a registered user, on the login page, I click on the "Quên mật khẩu" button: 1. Click in the input box but do not fill it out or leave email address empty and click "Lưu" button, then an error message will be displayed “Bạn cần nhập địa chỉ email khôi phục mật khẩu!” 2. Enter the email address, if my email address is NOT correct with data on database, then I can see an error message “Địa chỉ email khôi phục mật khẩu chưa đúng!”. 3. Enter the email address, if my email address is correct with data on database, I can click the "Lưu" button then an email will be sent to my email with a verification code and I can see a message pop-up: "Mã xác thực đã được gửi đến email!" 4. Enter the verification code, if it's false, I can see a message pop-up: "Mã xác thực không hợp lệ!" then can re-enter this verification code for 4 times. 5. Click in the input box but do not fill it out or leave "Mã xác thực" empty and click "Lưu" button, then an error message will be displayed “Bạn cần phải nhập mã xác thực!" 6. Enter the verification code, if it's true, I can see a message pop-up: "Mã xác thực hợp lệ!" then can reset the password. 6. Enter a new password, click "Lưu" to save and active this account with the new password. 7. Click in the input box but do not fill it out or leave "Nhập lại mật khẩu mới" empty and click "Lưu" button, then an error message will be displayed “Bạn cần phải nhập mã xác thực!" 8. Given that I am a registered user, after reseting password, when I log in on the next time with this new password, I can log in successfully to use all the authenticated functions. | high | 1 | FE, BE, UI | Done
5 | First Registration Approval | Admin (Boss) | approve the first login for employees | I can ensure authorized access to the system and maintain data integrity | 1. Given that I am an admin, when I click the "Phê duyệt đăng ký" button, navigate to "Phê duyệt đăng ký" page, and view detailed information for each new employee account, then I can: 2. Click verify icon, then I can see a message "Đã phê duyệt thành công" and this account can be able to use all the authenticated functions. 3. Click dustbin icon, then I can see a message "Đã từ chối phê duyệt" and this account cannot log in to this system to use all the authenticated functions until approving. | high | 1 | FE, BE, UI | Done
6 | Data Management | User (Boss, Leader, Staff) | add customer data | staff can have the detailed customer information | Given that I am a registered user, when on the "Quản lý khách hàng" page, click the "Tạo mới" button, enter customer information: Họ và tên, Số Điện Thoại, Mã khách hàng, Mã cuộc gọi, Mã nhân viên phụ trách, Kiểu dữ liệu, Trạng thái khách hàng: 1. Enter all required information, click 'Tạo mới" button, then I can see the updated customer list page after adding with a message pop-up "Tạo mới khách hàng thành công!" 2. Click "X" icon, then I will back to the "Quản lý khách hàng" page without any changes. 3. Click in the input box but do not fill it out or leave "Họ và Tên" empty and click "Tạo mới" button, then an error message will be displayed “Bạn cần phải nhập họ tên!” 4. Click in the input box but do not fill it out or leave "Số Điện Thoại" empty and click "Tạo mới" button, then an error message will be displayed “Bạn cần phải nhập số điện thoại!” 5. Click in the input box but do not fill it out or leave "Mã Khách Hàng" empty and click "Tạo mới" button, then an error message will be displayed “Bạn cần phải nhập mã khách hàng!" 6. Click in the input box but do not fill it out or leave "Mã Cuộc Gọi" empty and click "Tạo mới" button, then an error message will be displayed “Bạn cần phải nhập mã cuộc gọi!” 7. Click in the input box but do not fill it out or leave "Mã Nhân Viên Phụ Trách" empty and click "Tạo mới" button, then an error message will be displayed “Bạn cần phải nhập mã nhân viên phụ trách!” 8. Click in the input box but do not fill it out or leave "Kiểu Dữ Liệu" empty and click "Tạo mới" button, then an error message will be displayed “Bạn cần phải nhập kiểu dữ liệu!” 9. Click in the input box but do not fill it out or leave "Trạng Thái Khách Hàng" empty and click "Tạo mới" button, then an error message will be displayed “Bạn cần phải nhập trạng thái khách hàng!” 10. Enter wrong phone number format (not form 10 to 12 characters) then an error message will be displayed “Số điện thoại sai định dạng!” | high | 2 | FE, BE, UI | Done
7 |  | User (Boss, Leader, Staff) | edit customer data | I can update information of the customer | Given that I am a registered user, when on the "Quản lý khách hàng" page, click the "Chỉnh sửa" icon, enter customer information: Họ tên, Số Điện Thoại, Mã khách hàng, Mã cuộc gọi, Mã nhân viên phụ trách, Kiểu dữ liệu, Trạng thái khách hàng: 1. Enter all required information, click "Chỉnh sửa" button, then I can see the updated customer list page after editing. 2. Click "X" icon, then I will back to the "Quản lý khách hàng" page without any changes. 3. Leave "Họ Và Tên" empty, click "Chỉnh sửa" button, then an error message will be displayed “Bạn cần phải nhập họ tên!” 4. Leave "Số Điện Thoại" empty, click "Chỉnh sửa" button, then an error message will be displayed “Bạn cần phải nhập số điện thoại!” 5. Leave "Mã Khách Hàng" empty, click "Chỉnh sửa" button, then an error message will be displayed “Bạn cần phải nhập mã khách hàng!" 6. Leave "Mã Cuộc Gọi" empty, click "Chỉnh sửa" button, then an error message will be displayed “Bạn cần phải nhập mã cuộc gọi!” 7. Leave "Mã Nhân Viên Phụ Trách" empty, click "Chỉnh sửa" button, then an error message will be displayed “Bạn cần phải nhập mã nhân viên phụ trách!” 8. Leave "Kiểu Dữ Liệu" empty, click "Chỉnh sửa" button, then an error message will be displayed “Bạn cần phải nhập kiểu dữ liệu!” 9. Leave "Trạng Thái Khách Hàng" empty, click "Chỉnh sửa" button, then an error message will be displayed “Bạn cần phải nhập trạng thái khách hàng!” 10. Edit wrong phone number format (not form 10 to 12 characters) then an error message will be displayed “Số điện thoại sai định dạng!” | high | 2 | FE, BE, UI | Done
8 |  | User (Boss, Leader, Staff) | add call data | staff can have the detailed call onformation for each customer | Given that I am a registered user, when on the "Quản lý cuộc gọi" page, click the "Tạo mới" button, enter call information: Số điện thoại, Mô tả, Mã nhân viên phụ trách, Ngày gọi, Thời gian bắt đầu, Thời gian kết thúc, Thời lượng cuộc gọi, Trạng thái cuộc gọi: 1. Enter all required information, click "Tạo mới" button, then I can see the updated call list page after adding with "Mã cuộc gọi" is auto created, then a message pop-up is displayed "Tạo mới cuộc gọi thành công!" 2. Click "X" icon, then I will back to the "Quản lý cuộc gọi" page without any changes. 3. Click in the input box but do not fill it out or leave "Số Điện Thoại" empty, then an error message will be displayed “Bạn cần phải nhập mã cuộc gọi!” 4. Click in the input box but do not fill it out or leave "Mô Tả" empty, then an error message will be displayed “Bạn cần phải nhập mô tả!” 5. Click in the input box but do not fill it out or leave "Mã Nhân Viên Phụ Trách" empty, then an error message will be displayed “Bạn cần phải nhập mã nhân viên phụ trách!” 6. Click in the input box but do not fill it out or leave "Ngày Gọi" empty, then an error message will be displayed “Bạn cần phải nhập ngày gọi!" 7. Click in the input box but do not fill it out or leave "Thời Gian Bắt Đầu" empty, then an error message will be displayed “Bạn cần phải nhập thời gian bắt đầu!” 8. Click in the input box but do not fill it out or leave "Thời Gian Kết Thúc" empty, then an error message will be displayed “Bạn cần phải nhập thời gian kết thúc!” 9. Click in the input box but do not fill it out or leave "Thời Lượng Cuộc Gọi" empty, then an error message will be displayed “Bạn cần phải nhập thời lượng cuộc gọi!” 10. Click in the input box but do not fill it out or leave "Trạng Thái Cuộc Gọi" empty, then an error message will be displayed “Bạn cần phải nhập trạng thái cuộc gọi!” 11. Enter wrong phone number format (not form 10 to 12 characters) then an error message will be displayed “Số điện thoại sai định dạng!” | high | 2 | FE, BE, UI | Done
9 |  | User (Boss, Leader, Staff) | edit call data | I can update onformation of the call for each customer | Given that I am a registered user, when on the "Quản lý cuộc gọi" page, click the edit icon, edit call information: Số điện thoại, Mô tả, Mã nhân viên phụ trách, Ngày gọi, Thời gian bắt đầu, Thời gian kết thúc, Thời lượng cuộc gọi, Trạng thái cuộc gọi: 1. Click "Chỉnh sửa" button, then I can see the updated call list page after editting with a message pop-up "Sửa thông tin cuộc gọi thành công!" 2. Click "X" icon, then I will back to the "Quản lý cuộc gọi" page without any changes. 3. Leave "Số Điện Thoại" empty, then an error message will be displayed “Bạn cần phải nhập mô tả!” 4. Leave "Mô Tả" empty, then an error message will be displayed “Bạn cần phải nhập mô tả!” 4. Leave "Mã Nhân Viên Phụ Trách" empty, then an error message will be displayed “Bạn cần phải nhập mã nhân viên phụ trách!” 5. Leave "Ngày Gọi" empty, then an error message will be displayed “Bạn cần phải nhập ngày gọi!" 6. Leave "Thời Gian Bắt Đầu" empty, then an error message will be displayed “Bạn cần phải nhập thời gian bắt đầu!” 7. Leave "Thời Gian Kết Thúc" empty, then an error message will be displayed “Bạn cần phải nhập thời gian kết thúc!” 8. Leave "Thời Lượng Cuộc Gọi" empty, then an error message will be displayed “Bạn cần phải nhập thời lượng cuộc gọi!” 9. Leave "Trạng Thái Cuộc Gọi" empty, then an error message will be displayed “Bạn cần phải nhập trạng thái cuộc gọi!” 10. Edit wrong phone number format (not form 10 to 12 characters) then an error message will be displayed “Số điện thoại sai định dạng!” | high | 2 | FE, BE, UI | Done
10 | Advance Data Management | User (Boss, Leader, Staff) | search for customer data by customer phone | I can efficiently access and manage customer information | Given that I am a registered user, when on the "Quản lý khách hàng" page: 1. Enter a complete "Số Điện Thoại" on the search bar, click the magnifying glass icon, then I can see a list of matching customer records, including customer data. 2. Enter a wrong "Số Điện Thoại" on the search bar, click the magnifying glass icon, then I can see an error message "Không có dữ liệu!" 3. Leave "Số Điện Thoại" on the search bar empty, click the magnifying glass icon, then I can see a list of matching customer records, including customer data. | high | 2 | FE, BE, UI | Done
11 |  | User (Boss, Leader, Staff) | filter customer data by call status: "Mới, Nhỡ, Kết nối, Kết thúc" | I can easily identify and prioritize customer interactions | Given that I am a registered user, when on the "Quản lý khách hàng" page, click on one of four call status options in the slide bar, then I can see a list of matching customer records, including call data. | high | 2 | FE, BE, UI | Done
12 |  | User (Boss, Leader, Staff) | download the customer data file on excel form | I can save this file for company resource purposes | 1. Given that I am a registered user when on the "Quản lý khách hàng" page, click the download icon then I can receive the customer data file in Excel form on my device | high | 2 | FE, BE, UI | Done
13 |  | User (Boss, Leader, Staff) | download the call data file on excel form | I can save this file for company resource purposes | 1. Given that I am a registered user when on the "Quản lý cuộc gọi" page, click the download icon then I can receive the call data file in Excel form on my device | high | 2 | FE, BE, UI | Done
14 | Boss/Leader Management | User (Boss, Leader) | delete customer data | staff do not need to contact with the customer | 1. Given that I am a registered user with role: Boss, Leader, when on the "Quản lý khách hàng" page, click the "Xóa" button, then I can see a confirm message “Bạn có chắc chắn muốn xóa khách hàng này?": 1. Click "OK" button, I can see the updated customer list after deleting with this customer data associated with call data for this customer has be deleted. 2. Click "Cancel" button, then I will remain on the current page without changes. | high | 3 | FE, BE, UI | Done
15 |  | User (Boss, Leader) | change the role of employee | this employee can use all the authenticated functions of this role | 1. Given that I am a registered user with role "Admin/ Lead" when, on the "Quản lý nhân sự" page, click the edit icon, change the role of this employee to one of three options [Admin, Lead, Employee], then I can see the updated employee list after changing with a message pop-up "Sửa thông tin nhân viên thành công!" . 2. When an employee's role is changed, this employee will receive a notification about it "Admin đã thay đổi vai trò của bạn thành Lead!" or "Admin đã thay đổi vai trò của bạn thành Employee!" 3. After updating the role, when logging in next time, that employee can no longer use the functions of the old role and can fully perform the functions of the new role. | high | 3 | FE, BE, UI | Done
16 |  | User (Boss, Leader) | change the status of employee | I can easily manage employee | 1. Given that I am a registered user with role "Admin/ Lead", when on the "Quản lý nhân sự" page, click the edit icon, change the status of this employee to Hoạt động/Tạm nghỉ/Dừng, click "Chỉnh sửa" button, then I can see the updated employee list after changing with a message pop-up "Sửa thông tin nhân viên thành công!" | high | 3 | FE, BE, UI | Done

## Sprint Backlog
Sprint | User story | Task | Owner | Status | Estimated effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
1 | As a new user, I want to register a new account | Create account registration form | UI team | Done | 16
|  | Validate user inputs and display error messages | DEV team | Done
|  | Send confirmation email to user | DEV team | Done
|  | Write unit tests | TEST team | Done
1 | As an admin, I want to approve the first login for employees | Create registration approval page for admin | UI team | Done | 16
|  | Create approve or reject GUI | DEV team | Done
|  | Write unit tests | TEST team | Done
1 | As a user, I want to log in to the system | Create login button on website | UI team | Done | 16
|  | Create login form | DEV team | Done
|  | Validate user credentials and display error messages | DEV team | Done
|  | Write unit tests | TEST team | Done
1 | As a user, I want to log out to the system | Create logout button | UI team | Done | 16
|  | Display logout message to user | DEV team | Done
|  | Write unit tests | TEST team | Done
1 DL 27/3 | As a user, I want to reset password | Create reset password button | UI team | Done | 16
|  | Send email to user | DEV team | Done
|  | Write unit tests | TEST team | Done
1 | As a user, I want to add customer data | Create add button | UI team | Done | 16
|  | Create add cusstomer data form | DEV team | Done
|  | Display error messages | DEV team | Done
|  | Write unit tests | TEST team | Done
1 | As a user, I want to edit customer data | Create edit button | UI team | Done | 16
|  | Create edit customer data form | DEV team | Done
|  | Write unit tests | TEST team | Done
1 | As a user, I want to add call data | Create add button | UI team | Done | 16
|  | Create add call data form | DEV team | Done
|  | Display error messages | DEV team | Done
|  | Write unit tests | TEST team | Done
2 DL 10/4 | As a user, I want to edit call data | Create edit button | UI team | Done | 16
|  | Create edit call data form | DEV team | Done
|  | Write unit tests | TEST team | Done
2 | As a user, I want to search for customer data by customer phone number | Create search customer data button | UI team | Done | 16
|  | Display search customer data | DEV team | Done
|  | Write unit tests | TEST team | Done
2 DL 17/4 | As a user, I want to filter customer data by call status (Mới, nhỡ, Kết nối, Kết thúc) | Create filter button | UI team | Done | 16
|  | Display filter data | DEV team | Done
|  | Write unit tests | TEST team | Done
2 | As a user, I want to download the customer data file on excel form | Create download button | UI team | Done | 12
|  | Display download data | DEV team | Done
|  | Write unit tests | TEST team | Done
2 DL 24/4 | As a user, I want to download the call data file on excel form | Create download button | UI team | Done | 12
|  | Display download data | DEV team | Done
|  | Write unit tests | TEST team | Done
3 | As a user, I want to delete customer data | Create delete button | UI team | Done | 12
|  | Display confirmation message to user | DEV team | Done
|  | Write unit tests | TEST team | Done
3 | As a user, I want to change the role of employee | Create change the role of employee form | UI team | Done | 16
|  | Display confirmation message to user | DEV team | Done
|  | Write unit tests | TEST team | Done
3 DL 8/5 | As a user, I want to change the status of employee | Create change the status of employee form | UI team | Done | 16
|  | Display confirmation message to user | DEV team | Done
|  | Write unit tests | TEST team | Done

## Sprint Plan
Sprint | User Story | Task | Story Points | Estimated Time | Assigned Team Member | Progress
1 | Register A New Account | Define and implement login based on user requirements | 2 | 4 hours | Frontend Developer | Done
1 | Register A New Account | Integrate login function with database | 3 | 6 hours | Backend Developer | Done
1 | First Registration Approval | Define and implement sign up based on user requirements | 2 | 4 hours | Frontend Developer | Done
1 | First Registration Approval | Integrate sign up function with database | 3 | 6 hours | Backend Developer | Done
1 | Login | Define and implement login based on user requirements | 2 | 4 hours | Frontend Developer | Done
1 | Login | Integrate login function with database | 3 | 6 hours | Backend Developer | Done
1 | Log out | Define and implement login based on user requirements | 2 | 8 hours | Frontend Developer | Done
1 | Log out | Integrate login function with database | 3 | 10 hours | Backend Developer | Done
1 | Reset password | Define and implement sign up based on user requirements | 2 | 4 hours | Frontend Developer | Done
1 | Reset password | Integrate sign up function with database | 3 | 6 hours | Backend Developer | Done
1 | Testing and verification | Test and verify register a new account | 2 | 4 hours | Tester | Done
1 | Testing and verification | Test and verify first registration approval | 2 | 4 hours | Tester | Done
1 | Testing and verification | Test and verify log in | 2 | 4 hours | Tester | Done
1 | Testing and verification | Test and verify reset password | 2 | 4 hours | Tester | Done
1 | Testing and verification | Test and verify log out | 2 | 4 hours | Tester | Done
1 | Add customer data | Define and implement add data based on user requirements | 3 | 6 hours | Frontend Developer | Done
1 | Add customer data | Integrate add data with database | 4 | 8 hours | Backend Developer | Done
1 | Edit customer data | Define and implement delete product based on user requirements | 3 | 6 hours | Frontend Developer | Done
1 | Edit customer data | Integrate delete product with database | 4 | 8 hours | Backend Developer | Done
1 | Add call data | Define and implement add data based on user requirements | 3 | 6 hours | Frontend Developer | Done
1 | Add call data | Integrate add data with database | 4 | 8 hours | Backend Developer | Done
1 | Edit call data | Define and implement delete product based on user requirements | 3 | 6 hours | Frontend Developer | Done
1 | Edit call data | Integrate delete product with database | 4 | 8 hours | Backend Developer | Done
1 | Testing and verification | Test and verify add customer data | 2 | 4 hours | Tester | Done
1 | Testing and verification | Test and verify edit customer data | 2 | 4 hours | Tester | Done
1 | Testing and verification | Test and verify add call data | 2 | 4 hours | Tester | Done
1 | Testing and verification | Test and verify edit call data | 2 | 4 hours | Tester | Done
2 | Search for customer data by customer phone number | Define and implement search for customer data by customer phone number | 3 | 6 hours | Frontend Developer | Done
2 | Search for customer data by customer phone number | Integrate search for customer data by customer phone number with database | 4 | 8 hours | Backend Developer | Done
2 | Filter customer data by call status (Mới, Nhỡ, Kết nối, Kết thúc) | Define and implement filter customer data by call status (Mới, Nhỡ, Kết nối, Kết thúc) | 3 | 6 hours | Frontend Developer | Done
2 | Filter customer data by call status (Mới, Nhỡ, Kết nối, Kết thúc) | Integrate filter customer data by call status (Mới, Nhỡ, Kết nối, Kết thúc) with database | 4 | 8 hours | Backend Developer | Done
2 | Testing and verification | Test and verify search for customer data by customer phone number | 2 | 4 hours | Tester | Done
2 | Testing and verification | Test and verify filter customer data by call status (Mới, Nhỡ, Kết nối, Kết thúc) | 2 | 4 hours | Tester | Done
2 | Download the customer data file on excel form | Define and implement download the customer data file on excel form | 3 | 6 hours | Frontend Developer | Done
2 | Download the customer data file on excel form | Integrate download the customer data file on excel form with database | 4 | 8 hours | Backend Developer | Done
2 | Download the call data file on excel form | Define and implement download the call data file on excel form | 3 | 6 hours | Frontend Developer | Done
2 | Download the call data file on excel form | Integrate download the call data file on excel form with database | 4 | 8 hours | Backend Developer | Done
2 | Testing and verification | Test and verify download the customer data file in excel form | 2 | 4 hours | Tester | Done
2 | Testing and verification | Test and verify download the call data file in excel form | 2 | 4 hours | Tester | Done
3 | Delete customer data | Define and implement delete customer data | 3 | 6 hours | Frontend Developer | Done
3 | Delete customer data | Integrate checkout with database | 4 | 8 hours | Backend Developer | Done
3 | Change the role of employee | Define and implement change the role of employee | 3 | 6 hours | Frontend Developer | Done
3 | Change the role of employee | Integrate change the role of employee | 4 | 8 hours | Backend Developer | Done
3 | Change the status of employee | Define and implement change the status of employee | 3 | 6 hours | Frontend Developer | Done
3 | Change the status of employee | Integrate change the status of employee | 4 | 8 hours | Backend Developer | Done
3 | Testing and verification | Test and verify delete customer data | 2 | 4 hours | Tester | Done
3 | Testing and verification | Test and verify change the role of employee | 2 | 4 hours | Tester | Done
3 | Testing and verification | Test and verify change the status of employee | 2 | 4 hours | Tester | Done
Note on D1: Nhóm thống nhất thang điểm sử dụng, từ 1 đến 5 ======
Note on A16: dl 27/3 ======
Note on A28: dl 10/4 ======
Note on A34: dl 17/4 ======
Note on A40: dl 24/4 ======
Note on A49: dl 28/5 ======